## Slide 1: NordDRG Forum
Examples of
comments and deadlines

## Slide 2: This presentation
This presentation has been made from the national organizations point of view, but also other parties will benefit of it.
Forum users/parties in this presentation:
National organization = You
Main Program supplier = Datawell
Nordic Casemix centre

## Slide 3: Year 2016 deadlines
2016-01-29 Delivery of major update proposal for NordDRG (National organization)
2016-02-26 Delivery of minor update proposal for NordDRG (National organization)
2016-03-14 - 15 Expert group meeting (everybody)
2016-04-13 Delivery of national lists of DRG changes and technical changes to Nordic Casemix Centre (National organization)
2016-04-20 Delivery of national lists of DRG changes and technical changes to Main Program supplier (Nordic Casemix Center)
2016-05-04 Delivery of National Planning PL0-versions definition tables and a test grouper (if wished) with table of changes from previous year delivered to each national organization (Main Program supplier)
2016-05-18 Comments and corrections to National Planning 0-versions (National organization)
2016-06-01 Publication of National Planning version 1.0 definition tables to program suppliers (Nordic Casemix Centre)
2016-06-08 Publication of Planning version groupers (Main Program supplier)
2016-06-15 Publication of table of changes of definition tables of Planning versions (PL1) from previous year with each change linked to case at issue in List of Technical and DRG changes (Main Program supplier)
2016-06-30 Delivery of National ICD and NCSP versions to Nordic Casemix Centre (National organization)
2016-08-12 NCSP+ and ICD10+ update (Nordic Casemix Centre)
2016-08-25 - 26 Meeting of Nord DRG experts to complete NCSP+ and ICD10+ and check properties of new codes (everybody) and Comments and corrections to NCSP+ and ICD10+ mapping (National organization)
2016-09-02 Delivery of updated list of DRG changes and Technical changes for national versions to Nordic Casemix Center (National organization)
2016-09-09 Delivery of updated list of DRG changes and Technical Changes for national versions to software supplier (Nordic Casemix Center)
2016-09-23 Delivery of National PR0 definition tables with table of changes from PL1 version (Main Program supplier)
2016-10-07 Comments and corrections to National PR0 version (Nordic Casemix Centre and National organization)
2016-10-14 Publication of NordDRG National Production versions (PR 1.0) definition tables to program suppliers (Main Program supplier and Nordic Casemix Centre)
2016-11-04 Publication of Production version groupers (Main Program supplier)
2016-11-04 Publication of table of changes of definition tables of Producrion versions from previous year with each change linked to case at issue in the List of Technical and DRG changes (Main Program supplier)

## Slide 4: Deadline by 2016-01-29
Delivery of major update proposal for NordDRG (National organization)
Your comment to Forum:
“Major update proposals delivered to Nordic Casemix Centre”

## Slide 5: Deadline by 2016-02-26
Delivery of minor update proposal for NordDRG (National organization)
Your Comment to Forum:
“Minor update proposals delivered to Nordic Casemix Centre”
Notes: ONCE AGAIN, after sending minor update proposals, you make your comment to Forum, which is ”Minor update proposals delivered to xxx”

## Slide 6: 2016-03-14 - 15
Expert group meeting (everybody)
Comments to forum depends on the meeting.
If you have during the meeting promised to do something for your national version, after completing it, make a comment to forum.

## Slide 7: Deadline by 2016-04-13
Delivery of national lists of DRG changes and technical changes to Nordic Casemix Centre (National organization)
Your comment to Forum:
“National lists of DRG changes and technical changes sent to Nordic Casemix Centre”

## Slide 8: Deadline by 2016-04-20
Delivery of national lists of DRG changes and technical changes to Main Program supplier (Nordic Casemix Center)
Nordic Casemix Centre´s comment to Forum:
“National lists of DRG changes and technical changes delivered to Datawell”

## Slide 9: Deadline by 2016-05-04
Delivery of National Planning PL0-versions definition tables and a test grouper (if wished) with table of changes from previous year delivered to each national organization (Main Program supplier)
Datawell´s comment to Forum:
“National Planning PL0-version definition tables (and a test grouper) with previous year delivered to XX”

## Slide 10: Deadline by 2016-05-18
Comments and corrections to National Planning 0-versions (National organization)
Your comment to Forum:
“XX would like the following changes to be made….”
OR
“XX has no comments, nor corrections”

## Slide 11: Deadline by 2016-06-01
Publication of National Planning version 1.0 definition tables to program suppliers (Nordic Casemix Centre)
Nordic Casemix Centre´s comment to Forum:
“National Planning version 1.0 definition tables published”

## Slide 12: Deadline by 2016-06-08
Publication of Planning version groupers (Main Program supplier)
Datawell´s comment to Forum:
“Planning version groupers published”

## Slide 13: Deadline by 2016-06-15
Publication of table of changes of definition tables of Planning versions (PL1) from previous year with each change linked to case at issue in List of Technical and DRG changes (Main Program supplier)
Datawell´s comment to Forum:
“Table of changes of definition tables of PL1 published”

## Slide 14: Deadline by 2016-06-30
Delivery of National ICD and NCSP versions to Nordic Casemix Centre (National organization)
Your comment to Forum:
“ICD and NCSP versions delivered to Nordic Casemix Centre”

## Slide 15: Deadline by 2016-08-12
NCSP+ and ICD10+ update (Nordic Casemix Centre)
Nordic Casemix Centre´s comment to Forum:
“NCSP+ and ICD10+ updated to Nordic Casemix Centre´s webpage”

## Slide 16: 2016-08-25-26
Meeting of Nord DRG experts to complete NCSP+ and ICD10+ and check properties of new codes (everybody) and Comments and corrections to NCSP+ and ICD10+ mapping (National organization)
Your comment to Forum:
“XX would like the following changes to be made….”
OR
“XX has no comments, nor corrections”

## Slide 17: Deadline by 2016-09-02
Delivery of updated list of DRG changes and Technical changes for national versions to Nordic Casemix Centre (National organization)
Your comment to Forum:
“Updated list of DRG and Technical changes delivered to Nordic Casemix Centre”

## Slide 18: Deadline by 2016-09-02
Delivery of updated list of DRG changes and Technical Changes for national versions to software supplier (Nordic Casemix Center)
Nordic Casemix Centre´s comment to Forum:
“Updated list of DRG and Technical changes delivered to Datawell”

## Slide 19: Deadline by 2016-09-23
Delivery of National PR0 definition tables with table of changes from PL1 version (Main Program supplier)
Datawell´s comment to Forum:
“National PR0 definition table and table of changes from PL1 version delivered”

## Slide 20: Deadline by 2016-10-07
Comments and corrections to National PR0 version (Nordic Casemix Centre and National organization)
Nordic Casemix Centre´s comment to Forum:
“Nordic Casemix centre would like the following changes to be made…” OR
“Nordic Casemix Centre has no comments nor corrections”
Your comment to Forum:
“XX would like the following changes to be made….”
OR
“XX has no comments nor corrections”

## Slide 21: Deadline by 2016-10-14
Publication of NordDRG National Production versions (PR 1.0) definition tables to program suppliers (Main Program supplier and Nordic Casemix Centre)
Datawell´s / Nordic Casemix Centre´s comment to Forum:
“NordDRG National Production versions (PR 1.0) definition tables to program suppliers published”

## Slide 22: Deadline by 2016-11-04
Publication of Production version groupers (Main Program supplier)
Datawell´s comment to Forum:
“Production version groupers published”

## Slide 23: Deadline by 2015-11-04
Publication of table of changes of definition tables of Production versions from previous year with each change linked to case at issue in the List of Technical and DRG changes (Main Program supplier)
Datawell´s comment to Forum:
“Table of changes of definition tables of Production versions from previous year with each change linked to case at issue in the List of Technical and DRG changes published”

## Slide 24: In case of an error in codes…
Datawell´s comment to Forum:
”Datawell has found an error concerning……
Additional version is required. Shall we proceed with an additional version?”
Your reply to the comment on Forum:
”XX permits proceeding with an additional version”